LENDERMATCH™  ·  CHANGE REQUEST

Round 4 — New Platform Additions

React + Supabase implementation  ·  August 2026  ·  Confidential

Draft for review — not yet approved This proposal covers the requests sent on 4, 17 and 18 August 2026, including the document requirements attachment. Estimates are firm hours for the scope listed, with QA and testing included, and are built on the platform as delivered and currently live.

1.  Executive summary

1.1  Estimate

Twenty-six requested items, sized against the delivered platform and organised into five delivery phases. Round 3 was 64 hours; this round covers considerably more ground, adding four new pieces of the platform — rental-income qualification, the document-requirements engine, AI-generated lender notes and sales tax on invoicing — alongside roughly twenty-five field, label and filter changes.

| Phase | Focus | Hours |
| --- | --- | --- |
| Phase 1 | Create Deal fields, labels and lender filters | 14 |
| Phase 2 | Email provider, brokerage rates and marketplace rules | 18 |
| Phase 3 | Suspensions and the Resources section | 15 |
| Phase 4 | Rental income and the document-requirements list | 17 |
| Phase 5 | AI lender notes and invoicing | 19 |
| Across all | Migrations, bilingual copy, testing and deployment | 5 |
| TOTAL | Full Round 4 engagement | 88 h |

Firm total: 88 hours, development and QA included — two weeks from approval. Phases are independently deployable and can be invoiced as delivered, the same way Round 3 ran.

1.2  One item is already built

The lender suspension rule confirmed on 4 August — no deals with a closing date inside 45 days or a COF date inside 14 days — is exactly the rating-penalty effect delivered in Round 3, including the admin-configurable day thresholds. Only the manual control, the audit trail and the broker side are new work, which is why suspensions are quoted at 8.5 hours rather than roughly twenty.

1.3  Phase order

The phases are ordered by dependency, not by preference. The document-requirements list keys off six fields that do not exist on the platform yet — HoldCo, spousal buyout, refinance plus improvements, foster care income, the child-support TDS checkbox and condo conversion — so the field work in Phase 1 has to land before Phase 4 can be built.

2.  Detailed breakdown

Every requested item, grouped by delivery phase, with firm hours.

Phase 1 — Create Deal fields, labels and lender filters

| Requested change | Hours |
| --- | --- |
| Property-tax preference checkboxes, with a lender filter for either Two checkboxes in the Property section plus the matching lender exclusion. | 1 |
| “HoldCo on title” checkbox | 0.25 |
| “Spousal buyout” and “Refinance plus improvements” checkboxes Added to Deal Information alongside Reverse Mortgage and First Time Home Buyer. | 0.5 |
| “First-Time Buyer” renamed to “First Time Home Buyer” | 0.25 |
| “Foster Care Income” added to the income checkboxes | 0.5 |
| “Condo conversion” added to the dwelling types | 0.5 |
| “Child support or alimony included in the TDS ratios” checkbox Placed under GDS/TDS. No lender filter, as requested. | 0.5 |
| Down-payment source and notes hidden on refinance and renewal Includes the “Foreign Income / Down Payment Country” label collapsing to “Foreign Income”. | 1.25 |
| Mobile home: year built and CSA seal, with both lender filters | 1.25 |
| Label changes and the work-permit 183-day warning Medical Professionals Program (Projected income), Hourly (Guaranteed hours, no OT/Bonus), Net Worth Program. | 0.75 |
| Lender sign-in prompt to set lending criteria Stops appearing once the lender has saved one filter. | 1.25 |
| “Select Lender” label on the create-account page | 0.25 |
| “Not on the list? Email support@lendermatch.ca” on both sign-up forms | 0.25 |
| Closing-survey questions reworded to “within the quoted timeframe” | 0.25 |
| Net Worth Program: “Annual Income” input with the lender-variation note | 0.5 |
| Lender filter: minimum income required for the Net Worth Program Restricts matches only when the lender has entered a minimum. | 1.25 |
| Carrying every new field through the lender filter system Saved filters, the filter side-panel, lender settings, the matching engine and both deal feeds. | 3.5 |
| Subtotal — Phase 1 | 14 h |

Phase 2 — Email provider, brokerage rates and marketplace rules

| Requested change | Hours |
| --- | --- |
| Move transactional email to SendGrid Twelve notification emails onto SendGrid dynamic templates you author yourselves, the Contact-Us form, the account emails onto SendGrid delivery, plus a short guide for writing the templates. | 6.5 |
| Platform bps editable per brokerage in the admin portal Applies to every invoice created after the change; invoices already issued are untouched. | 4.5 |
| “Which lender declined the loan?” dropdown, with the owned-group rule Required unless “Lender not shown” is ticked; the named lender cannot see the deal, and selecting RMG, MERIX or MCAP hides it from all three. Built so you can maintain the group list yourselves. | 5 |
| One offer per lender institution Once any user at a lender offers, the deal leaves their colleagues’ New and Maturing lists. | 2 |
| Subtotal — Phase 2 | 18 h |

Phase 3 — Suspensions and the Resources section

| Requested change | Hours |
| --- | --- |
| Broker and lender suspension Manual suspend and reinstate from the admin portal, automatic suspension after three contact-sharing attempts, a record of when and why each suspension happened, and the visibility rules on both sides. | 8.5 |
| Resources section, published from the admin portal New tab in the broker and lender headers, with the editor you already use for the legal pages. | 6.5 |
| Subtotal — Phase 3 | 15 h |

Phase 4 — Rental income and the document-requirements list

| Requested change | Hours |
| --- | --- |
| Rental-income qualification module The three rental categories, the 39/44 and 55/55 variants by transaction type, legal and non-legal suite, addback and offset, the percentage tiers with the automatic cascade, and the lender’s maximum addback and offset criteria. | 9 |
| Document-requirements list shown on submission All thirty-five conditional rules from your attachment, driven by what the broker entered, re-openable from the Deal Room and printable. | 8 |
| Subtotal — Phase 4 | 17 h |

Phase 5 — AI lender notes and invoicing

| Requested change | Hours |
| --- | --- |
| AI-generated lender notes on acceptance Your eleven sections in order, the broker’s own notes folded into the right section, your disclaimer above and the fixed closing paragraph left untouched, with a copy button. Property enrichment is excluded — see section 3. | 6.5 |
| Admin-editable invoice template Header, payment terms, tax and registration lines, remittance wording and footer, edited in the admin portal with a live preview. | 5 |
| Sales tax by province and territory An editable rate table, the registration numbers printed on the invoice, subtotal/tax/total on the PDF, and capturing a billing province for each lender — which the platform does not record today. | 7.5 |
| Subtotal — Phase 5 | 19 h |

Across all phases

| Requested change | Hours |
| --- | --- |
| Migrations, bilingual copy, testing and deployment Database migrations, English and French parity, automated test updates, staging verification and the production deploys for each phase. | 5 |
| Subtotal | 5 h |

3.  Two items we have not priced

Both are requests we can build. Neither should be quoted as a normal line item, for reasons worth putting in writing before you decide.

Showing the broker which lenders declined

The platform’s central rule is that identities stay hidden until an offer is accepted, and that rule is enforced in the database itself, not just on screen. Revealing which lenders passed on a deal reverses that rule in one direction: brokers would learn lender identities before accepting anyone. We can do it — it is roughly three hours — but it is a product decision about the promise the platform makes to lenders, not an implementation detail, so we would like it confirmed explicitly rather than assumed.

Two smaller alternatives, if the goal is to reassure the broker rather than to name names: a count (“four lenders reviewed this deal and passed”), or the names released only after the deal closes. Also worth clarifying: “no matches in two days” could mean no offers, or no lenders whose filters match — those are different messages.

Pulling property details from realtor.ca

realtor.ca belongs to CREA, its terms prohibit automated collection, it is behind bot protection, and there is no open API. The legitimate route is a CREA data licence (DDF), which is a commercial agreement your brokerage would hold rather than something we can code around. Anything built without it would work until it stopped, without warning.

So the AI lender notes are quoted using the information the broker already enters, which covers refinances and renewals exactly as you described. If you have or can obtain DDF access, we will scope the purchase-side enrichment on top of it.

4.  Decisions we need from you

Each of these changes what gets built rather than how long it takes. Answers before the relevant phase begins keep the schedule intact; an answer that changes a rule’s shape is re-estimated rather than absorbed.

01.  Property taxes — one choice or two checkboxes?

The two options are mutually exclusive in practice. Should they behave as a single either/or choice, or as two checkboxes where leaving both empty means “not specified”?

02.  Per-brokerage bps — one rate or three?

A single override for a brokerage, or a full set of three, four and five by term as today?

03.  Which province governs the sales tax?

The invoice is billed to the lender, and the lender’s province is not necessarily the property’s. We would rather your accountant set the rule than have us pick one. We also need the registration numbers that must appear on the invoice, and which taxes you are registered to charge.

04.  Invoice template — text or layout?

Editing the wording inside the current layout is the five hours quoted. Full control over layout and ordering is a different build, roughly twice that.

05.  Rental income — how should a lender’s maximum match?

If a broker checks 80% addback and a lender’s maximum is 90%, we read that as a match. If the lender’s maximum is 50% and the broker only checked 80% and above, no match. Please confirm that reading, and what the taxes-and-heat exclusion does to it.

06.  Suspensions — how long, and counted how?

How long does an automatic suspension last, and over what period are the attempts counted — per deal, per lender, or ever? The 4 August note says more than two attempts and the 17 August email says three separate messages; worth settling in one sentence.

07.  Suspensions — what about deals already accepted?

If a broker is suspended while a deal has an accepted offer and a live invoice, there is a lender on the other side counting on it. Does that deal continue?

08.  Declines — do they apply to a whole lender?

If one person at a lender declines a deal, does it disappear for their colleagues too, or only for them?

09.  The document list in French

Everything user-facing on the platform is bilingual. The list is about 1,300 words of underwriting vocabulary. We can translate it (included above), you can supply the French, or this one screen can ship in English as a documented exception.

10.  Resources — one feed or two?

Shared content for brokers and lenders, or separate sections? And do posts need images or attachments?

11.  SendGrid — the key needs moving

The API key was added to Vercel, but the emails are sent by the Supabase side of the platform, which never sees Vercel’s settings. It needs to be added there instead; we will handle it, but the Vercel copy is doing nothing today. One limitation to know: your notification emails can use SendGrid templates, but the account emails — sign-up confirmation, password reset — are generated by the login system and will keep using its own templates, which stay editable where they are now.

5.  Schedule

| Week | Delivered |
| --- | --- |
| Week 1 | Phases 1 and 2 to staging for your review, then to production; Phase 3 under way |
| Week 2 | Phase 3 completed, Phases 4 and 5 built; full regression pass and production deploy |

Two weeks is achievable, with one condition The schedule has no slack for waiting on answers, and two of them sit on your side rather than ours: Phase 5 cannot start without the tax rule and your registration numbers, and Phase 4’s document list needs the French decision. If those arrive at approval, two weeks holds. If they arrive in week two, the date moves — which we would rather say now than then.

6.  Assumptions

Built on the platform as delivered — accounts, permissions, the matching engine, notifications and email, scheduled jobs, file storage, invoice generation and the contact-information screening are all in place and are not re-charged here.

Hours include development and testing. Every phase is verified on staging before it reaches production.

New wording ships in English and French, except where decision 09 says otherwise.

SendGrid domain verification and DNS are completed on your side; we use the verified sender.

The AI lender notes are a draft for the broker to review before sending — as your own disclaimer says — not a verified submission package.

Sales tax is applied from an agreed date forward. Invoices already issued are left exactly as they are.

Next step.  On written approval of this proposal, and with the decisions in section 4 answered, Phase 1 begins immediately and each phase is invoiced as delivered.